## Sheet1
14 May	15 May	16 May	17 May	18 May	19 May	20 May	21 May	22 May	23 May	24 May	25 May
M	T	W	T	F	S	S	M	T	W	T	F
	Deliverable 1				Deliverable 2				Deliverable 3		Final Presentation
Define User Story (All)
Define UI Flow (All)
Define Schema (All)
Define API (Michael)
	Build Project Schema (Orit)
			Build API (Orit)
	Build User Schema (Will)
			Token Auth (Will)
	Build Routes (Michael)
		Build Math Functions (Michael)
	Build Wireframe (Caroline/Chris)
		Visual Mockups (Caroline)
		Functional Wireframe (Chris)
				Merge Wireframe/Mockup (Caroline/Chris)
					Package/Heroku Deployment (Michael)
					PDFKit Feature (Will)
					Full Testing (Chris)
								Final Merges (All)
									Presentation Build